## Risico raport
1. BASIC RISK INFORMATION |  |  |  |  | 2. RISK ASSESSMENT INFORMATION |  |  |  |  | 3. RISK RESPONSE INFORMATION
Risk Number | Risk Description / Risk Event Statement | Responsible | Date Reported day-month-year | Last Update day-month-year | Impact H / M / L | Impact Description | Probability H / M / L | Timeline N/M/F | Status of Response | Completed Actions | Planned Future Actions | Risk Status Open / Closed / Moved to Issue
R 1 | Huidige domein waarop de tool word gehost kan niet voldoen aan de eisen gesteld door het gebruikte framework, en daarom kans op wisselvallig gedrag | Instelling | 2017-04-04 | 2017-04-13 | M | Nieuwe manier vinden om het huidige domein zo betrouwbaar mogelijk te maken. | L | N/A | Afwachting | 4-apr-2017: Risico aangegeven 7-apr-2017: Formeel aangegeven met uitleg | N/A | Open
R 2 | Ontwikkelde tool kan niet worden live gezet vanwegen richtlijnen van ROC Ter AA | Instelling | 2017-05-06 | 2017-06-30 | M | Instelling heeft contracten met bedrijf raet. Dit bedrijf ontwikkelt modules | M | N/A | Geweigerd | 31-juni-2017: Ontwikkeling van tool is defenitief op stop gezet. | N/A | Closed
R 3
R 4
R 5
R 6
R 7
R 8
R 9
R 10
R 11
R 12
R 13
R 14
R 15
R 16
R 17
R 18
R 19
R 20
R 21
R 22
R 23
R 24
R 25
R 26
R 27
R 28
R 29
R 30
R 31
R 32
R 33
R 34
R 35
R 36
R 37
R 38
R 39
R 40
R 41
R 42
R 43
R 44
R 45
R 46
R 47
R 48
R 49
R 50
R 51
R 52
R 53
R 54
R 55
R 56
R 57
R 58
R 59
R 60
R 61
R 62
R 63
R 64
R 65
R 66
R 67
R 68
R 69
R 70
R 71
R 72
R 73
R 74
R 75
R 76
R 77
R 78
R 79
R 80
R 81
R 82
R 83
R 84
R 85
R 86
R 87
R 88
R 89
R 90
R 91
R 92
R 93
R 94
R 95
R 96
R 97
R 98
R 99
R 100